## Dashboard
ATLAS Core Open Issues |  |  |  |  | ATLAS Usecase/Node Open Issues
Count of Severity | Column Labels |  |  |  | Count of Severity | Column Labels
Row Labels | major | Grand Total |  |  | Row Labels | critical | major | Grand Total
ATLAS Framework | 1 | 1 |  |  | ATLAS General Usecase | 2 |  | 2
Grand Total | 1 | 1 |  |  | ATLAS Node | 1 | 2 | 3
[5 empty] | Grand Total | 3 | 2 | 5
Count of Status | Column Labels
Row Labels | NEW | RE_OPENED | UNCONFIRMED | Grand Total
bhavani_s@hcl.com | 1 |  |  | 1
gnanaprasanna-r@hcl.com |  |  | 1 | 1
jaiganesh_d@hcl.com |  | 1 |  | 1
jeyaprabu.m@hcl.com | 1 |  |  | 1
mamtha.d@hcl.com | 1 | 1 | 19 | 21
pradeepa.j@hcl.com |  | 1 | 1 | 2
sivarama.k@hcl.com | 5 |  |  | 5
SSangineedi@hcl.com | 6 |  | 1 | 7
thadukamadla.r@hcl.com |  | 1 |  | 1
veeraganesh.v@hcl.com | 2 |  |  | 2
Grand Total | 16 | 4 | 22 | 42

## BugList
Bug ID | Product | Version | Component | Severity | Status | Summary | Assignee | Reporter | Planned effort | Actual effort
6270 | ATLAS | ATLAS 0.8.0 | ATLAS Node | major | NEW | extract comments from ms word aspose-->CommentedOn field is showing incorrect details in debug window. | Mamtha Dharanipathy | Harshitha Pinnapareddy | 0 | 0
6271 | ATLAS | ATLAS 0.8.0 | ATLAS Node | major | NEW | extract comments from ms word aspose-->CommentedOn-->extracted comment is appending to the commented word | Mamtha Dharanipathy | Harshitha Pinnapareddy | 0 | 0
6205 | ATLAS | ATLAS 0.8.0 | ATLAS Node | critical | NEW | Delete 4 nodes-->restart the server-->Showing exception for one module-->do we need to start 4 times separately to know the files? | Sivarama Kiran | Harshitha Pinnapareddy | 0 | 0
6260 | ATLAS | ATLAS 0.8.0 | ATLAS Framework | major | NEW | Atlas: Execute comparison viewer use case-->upload reference images file -->it's showing Error message as file comparison failed due to -[Object Object]. | Mamtha Dharanipathy | Srinivasulu | 0 | 0
6261 | ATLAS | ATLAS 0.8.0 | ATLAS General Usecase | critical | NEW | Atlas: comparesion viewer usecase--> upload reference image file -->once clicked on compare image still it is in progress-->using Framework 0.7 kit. | Mamtha Dharanipathy | Srinivasulu | 0 | 0
6266 | ATLAS | ATLAS 0.8.0 | ATLAS General Usecase | critical | NEW | Atlas: Comparsion viewer usecase -> Unable to compare images, pages, files for comparsion viewer usecase in "Update framework 0.7" kit and issue exist in "Update Installer 0.7" kit". | Mamtha Dharanipathy | Srinivasulu | 0 | 0